## Sheet1
Risk Log
|  | 1 - Low | 1 - Low | 1 - Low
|  | 5 - High | 5 - High | 20 - High
Id | Description | Likelyhood | Impact | Risk Factor | Mitigation | Responsible | Follow up date | Status date | Status
1 | Lack of experience in testing that might lead to poor testing results | 3 | 2 | 6 | -Reading tutorials -Doing more excercises -Pair programming -Learning from experienced students. | Burim, John and Denis | 12/10/2018 reading, doing excercises and inquiring from experienced students done | 19/10/2018 First test done and passed | Initial
2 | Lack of cooperation that might lead to pressurizing some of our team members | 3 | 4 | 8 | -Inclusion communication -Enhancing our communication | John, Burim and Denis | 30/10/2018 We resolved the problem slowing down our application implementation all agreed to be fully committed | 15/11/2018 Usability Testing done (Guerrila testing) | Open
3 | Working on a tight time schedule might cause delay in delivery | 2 | 4 | 15 | -Drop some functionalities -Following our plan strictly -Committing ourselves more in this project | Burim, John and Denis |  |  | Open
4 | Lack of UI design experience which might lead to delivering a non user-friendly product | 2 | 2 | 4 | -Usability test -Reading tutorials | Burim, John, Denis | 12/12/2018 We managed to carryout Acceptance test. Some tests passed but others failed |  | Open